## "X" Matrix
Name of Team Here
|  |  |  | Train & Implement w/leadership buy-in / alignment | [13 empty] | AP
|  |  |  | Develop a Consumption Based Replenishment Model | [13 empty] | AP
|  |  |  | Define Maturity Continum | [13 empty] | AP
AP
AP
| l |  |  | Parts spend reduction | m |  |  | l | [9 empty] | AP |  | m |  | l |  |  | m
| m |  | l | Enable Ops driven kaizen culture across SCM | l | l | [11 empty] | AP |  | l | m |  | m
|  | l |  | Develop Shingo Roadmap (Attend Annual Shingo Conference) | m | m |  |  | m | [8 empty] | AP | m |  | l |  |  | m
|  |  | l | Increase presence outside of SCM |  |  | l | [10 empty] | AP | l |  | m
|  | m | l | Standardize Lean throughout US SCM |  |  |  |  | l | [8 empty] | AP | m | m | m | m | m | l | m
| 10% Reduction of SCM cost to captive | Define & Align Organization around Shingo Award Implementation Plan | Deploy Level 1 Supply Chain wide (Ops Office & Enterprise Pilots" (model cells) |  | Increase YOY Kaizen events from 24* to XX | Increase YOY Leadership kaizen participation from X% to 100% | Increase YOY Enterprise engagement activity from X to X | Reduce Parts cost per unit vs. 100% new from x to x | Increase SCM ALPS Level 1 certifitied departments from 0 to X | [9 empty] | Team Member Names Here | Team Member Names Here | Team Member Names Here | Team Member Names Here | Team Member Names Here | Team Member Names Here | Team Member Names Here | Team Member Names Here | Team Member Names Here
|  |  | l | Deploy a Lean Production System at [company] globally (incorporate TPS fully) (3-5 yrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | l | Primary Responsibility
|  | l |  | Shingo Award Winning Supply Chain | [14 empty] | m | Secondary Responsibility
| l |  |  | Reduce SCM Cost to Captive by 25%
Annual
Improvement
Priorities
Targets To Improve
Breakthrough Objectives (3 year)
Annual
Objectives
Annual
Improvement
Priorities
Breakthrough Objectives
Targets To Improve
Breakthrough
Objectives
3-5 Years
Metrics (TTI's) - Targets To Improve
Targets To Improve

## Org Level TTI List
No. | Annual Improvement Priority | Target to Improve | 2012 JOP | 2012 | YTD | Jan | Feb | Mar | Aprl | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Year End Target | Msmt. Owner
AIP 1 | #REF! | Increase YOY Kaizen events from 24* to XX |  | Plan
Act / Fcst
AIP 2 | Train & Implement w/leadership buy-in / alignment | Increase SCM ALPS Level 1 certifitied departments from 0 to X |  | Plan | [15 empty] | l
|  |  |  | Act / Fcst | [15 empty] | m
AIP 3 | Develop Shingo Roadmap (Attend Annual Shingo Conference) | Increase SCM ALPS Level 1 certifitied departments from 0 to X |  | Plan | [15 empty] | m
Act / Fcst
AIP 4 | Develop a Consumption Based Replenishment Model | Increase SCM ALPS Level 1 certifitied departments from 0 to X |  | Plan
|  |  |  | Act / Fcst | [15 empty] | Mary Ann Auster - Central Test Engineering Manager
AIP 5 | Parts spend reduction | 0 |  | Plan
Act / Fcst
AIP 6 | Enable Ops driven kaizen culture across SCM | 0 |  | Plan
Act / Fcst
AIP 7 | Standardize Lean throughout US SCM | 0 |  | Plan
Act / Fcst
AIP 8 | Increase presence outside of SCM | 0 |  | Plan
Act / Fcst
AIP 9 | #REF! | 0 |  | Plan
Act / Fcst
AIP 10 |  |  |  | Plan
Act / Fcst
Note on C3: enter the exact TTI from the bowler
Note on D3: Enter the jumping off point measurement for the TTI. Enter a comment if anything other than the March MTD number was used here. Notes: this is the measurement of the process at the close of the previous Fiscal year. Since the final target will be measured relative to this JOP, it is important that ir accurately reflects where we left the previous year and can be compared meaningfully with the cussrent year. Options for this measurement: - if slow, steady progress was made on the measurement throughout the year, the most appropriate measurment is March MTD. - If an anomaly occured in the last month that made it non-representative of the process performance, the prevous month or an average of the last quarter can be used. - In very limited cases of flat perfomance or a measurement that can only be measured accurately on an annual basis, the previous year's average may be used.
Note on F3: update both plan and actual on a monthly basis -
Note on G3: plan: completed once at the start of the year and not adjusted after that - based on the action plan submitted Actual / Forecast: at the start of the SD cycle (the start of the year) this is the same as the plan update this monthly, all data up to the current month is actual, from the next month until the end of the year, this data is the forecast
Note on S3: must match the verbiage in the TTI
Note on T3: initials of the person responsible for supplying the measurement

## AIP # 1
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
#REF! | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
Increase YOY Kaizen events from 24* to XX
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 2
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Train & Implement w/leadership buy-in / alignment | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
Increase SCM ALPS Level 1 certifitied departments from 0 to X
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 3
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Develop Shingo Roadmap (Attend Annual Shingo Conference) | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
Increase SCM ALPS Level 1 certifitied departments from 0 to X
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 4
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Develop a Consumption Based Replenishment Model | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
Increase SCM ALPS Level 1 certifitied departments from 0 to X
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target key components of LSW:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 5
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Parts spend reduction | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
0
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 6
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Enable Ops driven kaizen culture across SCM | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
0
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 7
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Standardize Lean throughout US SCM | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
0
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 8
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Increase presence outside of SCM | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status: | Action plan and TTI on track
0
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## AIP # 9
ACTION PLAN | [19 empty] | Action plan and TTI on track
Improvement Priority Title: |  |  | Mgmt. Owner: | [15 empty] | Code: | Action Plan behind schedule, TTI not impacted - no C/M required
Increase presence outside of SCM | Support Team: | [18 empty] | Action Plan behind schedule, TTI Impacted - TTI C/M attached
Date:
TTI: | Status: |  | Status:
0
Current Situation Summary:
Action Step/ Kaizen Events | Owner | Assist | Planned Start | Planned Complete | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Capital Req'd | CY Impact | Ann'd Impact
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Identify and Target:
Prioritize:
Organize, Prepare, Plan:
Validate:
Plan:
Execute:
Review and Adjust
Total
[5 empty] | P = Planned |  |  |  | A = Actual |  |  |  | PA = completed in month planned
Enter the highlighted Cells
| Trend chart | [15 empty] | 1st LEVEL PARETO
| month | target | actual | [13 empty] | issue |  | qty
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
| Sep | [15 empty] | 2ND LEVEL PARETO
| Oct | [15 empty] | issue |  | qty
Nov
Dec
Note on E3: person in the group driving the project
Note on E4: enter the names of the team supporting the action plan
Note on T4: insert priority ID #
Note on T6: date of last update
Note on E11: Current situation/status of AIP or current risk associated with action plan
Note on A24: action steps, kaizen event or major task required to meet AIP
Note on B24: owner of this action - not necessarily the owner listed above
Note on D24: planned start date of this action
Note on F24: After the action plan is created, in the cells below, insert a "P" in the planned month for each action. On a monthly basis, update the cells with "A" in the correct month for any action completed. If a date slips, enter "P" in the new commit month, do not delete the old "P". Highlight the missed month in red.
Note on T24: Attempt to quantify the impact on the TTI - i.e. how far to the required improvement goal will this step move us

## CM Template
COUNTERMEASURE SHEET
Countermeasure For:
TTI #: |  | Description:
KPI #:
Problem Solving Data:
Root Cause Corrective Action:
Root Cause Problem Statement: |  |  |  | Countermeasure |  |  |  | Status
|  |  |  | What | Impact | Who | When
Enter the highlighted Cells
| Trend chart |  |  | 1st LEVEL PARETO
| month | target | actual | issue | qty
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
| Dec |  |  | 2ND LEVEL PARETO
| Jan |  |  | issue | qty
Feb
Mar
Note on B4: fill in one of these two depending on whether the countermeasure was driven by a TTI or KPI that is not improving as planned
Note on F4: insert the description of the TTI or the KPI that was missed
Note on A7: Either insert verbage to describe the problem or, preferrably, insert paretos or other charts that show how you got to the root cause of the problem.If verbiage is used, it must adequately describe the link between the top level measurement and the root cause. If graphs are to be used, include a trend chart and the appropriate pareto chart to show the most impactful root causes of the problem
Note on A9: Describe the root cause of the problem described above - there must be a direct link between the data shown in the "problem solving data" section above and the root cause described here
Note on L9: starus, e.g in process, complete, or delayed
Note on H10: decscribe the action to be taken to resolve the root cause to the left verify that there is a direct link with the Root Cause Described
Note on I10: enter the expected impact of the countermeasure. For example, the percentage of OTD improvement expected based on the action
Note on J10: name of person responsible for the corrective action
Note on K10: expected corrective action completion date

## About
This template is provided by OpExLearning.com
It cannot be sold or distributed without expressed written permission.
Learn more about Hoshin Kanri (X Matrix):
https://opexlearning.com/resources/about-peter-abilla/what-is-hoshin-kanri-in-lean-manufacturing/
How to use this template:
https://opexlearning.com/resources/hoshin-kanri-x-matrix-template-for-lean-policy-deployment/13775/